CDMP Research and Innovation Scheme (CRIS)

Mid-Term Review Report

| Principal Investigator: | Hongyang Zhang, Hongrui Yin, Man-On Pun |
| --- | --- |
| Project Title: | GeoLoc3D: Learning View-Invariant Localization from Unlabeled UAV Imagery via Tri-Modal 3D Reconstruction |
| Project Code: |  |
| Funding Duration: | March 1 to October 31, 2026 |
| Contact Number: | 18575689242 |
| E-Mail: | SimonPun@cuhk.edu.cn |

- Project Progress Summary (summarizing the main progress and finding, less than 1 page)

1.1 UAV–Satellite Collaborative 3D Scene Reconstruction

This project aims to connect UAV imagery, satellite imagery, and DSM priors through 3D reconstruction for view-invariant localization. At this stage, a reproducible UAV-side baseline has been established, including video preprocessing, VGGT/VGGT-Ω inference, COLMAP-compatible export, Gaussian Splatting optimization, and rendering-based evaluation. The project also clarified that VGGT-exported cameras and points are not equivalent to traditional COLMAP/SfM reconstruction, as they lack conventional multi-view tracks and reprojection constraints. This provides a basis for future fair comparison between learning-based and classical reconstruction methods.

Experiments show that view continuity and adjacent-frame overlap strongly affect reconstruction quality. On the Xueqing (CUHKSZ) sequence, using 46 continuous local frames instead of sparse full-video sampling improved results at the same 1,000-step budget: PSNR increased from 15.899 to 21.814 dB, SSIM from 0.2973 to 0.6504, and LPIPS decreased from 0.5080 to 0.2006. Cross-scene testing on a gym video recovered the basic layout and camera trajectory, although deformation and ghosting remain. A preliminary UAV–satellite alignment experiment also showed interpretable coarse geometric correspondence using a leveled UAV point cloud and manually selected matching points. This is currently a single-scene feasibility study rather than automatic registration or full fusion. Next, the project will add a traditional COLMAP baseline and introduce satellite and DSM constraints for improved global alignment.

1.2 Generalizable and Self-Supervised Cross-View Geo-Localization

The purpose of this research is to make cross-view geo-localization more practical in real-world UAV applications, where models often face large domain shifts across regions, seasons, weather conditions, and viewpoints, while accurately paired training data are expensive to obtain. To address these limitations, we explored two complementary directions: improving generalization to unseen environments and reducing dependence on labeled cross-view pairs.

For generalizable UAV CVGL, we developed InfoGeo, an object-centric, information-theoretic framework that learns view-invariant structural representations while suppressing view-specific noise. By selecting reliable visual concepts and modeling their structural relations across views, InfoGeo improves robustness under cross-region and multi-weather shifts. For self-supervised CVGL, we developed RSGeo, which learns from unpaired panoramas and satellite images. It first emphasizes reliable coarse structures, such as roads and building layouts, in synthesized views, and then progressively mines high-confidence real panorama-satellite pairs to learn fine-grained discriminative features. Experiments on CVUSA and CVACT show that RSGeo outperforms existing self-supervised methods and achieves strong cross-dataset generalization. Together, these two studies extend the project toward robust and scalable CVGL under unseen-domain and limited-label settings.

2. Outputs List

Publication (Only report outputs acknowledge funding from 1+1+1 CUHK-CUHK(SZ)-GDSTC Joint Collaboration Fund - Grant 2025A0505000079):

Hongyang Zhang, Maonan Wang, Ziyao Wang, Hongrui Yin, and Man-On Pun. " InfoGeo: Information-Theoretic Object-Centric Learning for Cross-View Generalizable UAV Geo-Localization." In Forty-third International Conference on Machine Learning. 2026.

Other works in progress:

Hongrui Yin, Hongyang Zhang, Ziyi Wang, and Man-On Pun. " Sketch First, Details Later: Reliability-Guided Self-Supervised Cross-View Geo-Localization." Submitted to Forty-first AAAI Conference on Artificial Intelligence. 2027.

Patent (if any)

Other outputs (only those acknowledged the support of the fund)

3. Supported Students

|  | Name | Student ID | Degree Level | Support Period | Role |
| --- | --- | --- | --- | --- | --- |
| 1 | Hongyang Zhang | 225010032 | PhD student |  | Project Leader |
| 2 | Hongrui Yin | 123090755 | Bachelor student |  | Research Assistant |

4. Other Comments (including risks of projects or adjustments)